## Guidance
Answer the following questions with community stakeholders to clarify your assumptions in vaccine planning, and to identify priority use/s and inputs for the site planning tool included on tabs 1 through 4.
1. Address critical assumptions by analyzing the local context. Determine needs and resource availability.
Mapping stakeholders and resources:
§ What local stakeholders should be included in the planning process to ensure alignment of roles and expectations? Mapping all relevant entities can help ensure smooth coordination and mitigate the risk of duplicative efforts.
§ Of the identified organizations, which ones are currently involved in providing vaccinations in your area, and to what extent?
o What types and sizes of vaccination sites are being set up and run by others?
o What coordinating functions are in place between stakeholders to plan coverage, inform progress? To what extent is data shared between stakeholders?
o Where are vaccination sites located or planned?
o What is the vaccination capacity and daily throughput of the current and planned sites?
Develop vaccine coverage goals:
§ What is the total, eligible catchment population within your locality?
§ What percent coverage level are you aiming to achieve at the local population level? (i.e. # number needing vaccination/total eligible population)
§ How soon do you hope to achieve desired coverage?
o Do you have different % and timeline goals for different sub-groups?
§ What groups in your community are currently eligible for vaccination?
o Who has already been vaccinated?
o Are there dedicated efforts, separate or adjacent to your operations, to specifically address the vaccination of certain sub-groups? Is another organization or coalition responsible for vaccinating certain sub-groups? (e.g., Local health department is solely responsible for homebound individuals)
o Approximately how many people are ineligible to receive vaccine? (# under 16 for Pfizer, # under 18 for Moderna and Johnson & Johnson)
§ What vaccine types will your site receive?
o How does dose number, timing and vaccine efficacy affect site throughput and planning?
o Are there plans for a different composition of vaccine types in the near future? If so, how will that affect your site planning?
2. Determine which groups or segments of the community you will focus on vaccinating, and identify viable sites to host vaccinations. Mapping tools can support stakeholder decision-making.
§ Are there areas where health care infrastructure is lacking and demand for vaccination is high? Are there areas within walking distance for community members, or where transportation options to and from a site exist?
§ Are there existing community-centers/public buildings (schools)/testing sites that can be leveraged to serve as COVID vaccination sites? Depending on your region and its weather considerations, are there parking lots or similar structures?
§ Review available demographic data and disease burden (COVID-19 cases). How do these profiles align with existing and planned sites? Are sites located in or accessible to communities bearing disproportionate burden?
3. Plan site layout for maximum throughput
Site Considerations:
§ Given the size of identified site/s, how many people can be vaccinated at one time while maintaining adequate physical distance between vaccinators, patients, and other staff?
§ What are vaccination station layouts that maximize the number of individuals who can be vaccinated in a given space?
Consider layouts, including how many seats can be included in each size site model. Keep in mind continued requirements for social distancing.
o Large: Mass vaccination site (i.e., stadium, park, convention center)
o Medium: School gym, churches
o Small: Federally Qualified Health Centers, mobile units
§ Build in flexibility for variable post-vaccination observation periods between standard and higher-risk groups
4. Determine how you will set-up, staff, and continuously operate vaccination.
§ What are the critical staffing considerations?
Basic structure for staffing within site includes: vaccine administration, clinical lead, registration, pharmacists, safety officer, data entry, queue management, traffic direction
§ What cadre of staff can do each of these tasks in your jurisdiction? I.e. which roles require specific skillsets or authorizations?
o Who in your state can serve as vaccinators?
o Consider maximizing efficiency and controlling costs. Consider liaising with local officials, community-based organizations, and medical providers to understand existing staff who may be repurposed for site tasks. Consider including care resource coordination services during registration or observation period [link to CRC operations]
§ What are financial costs for staff? Financial limitations to staffing? What is compensation for each cadre based on local pay scale and contracting fees
Disclaimer:
The ideas presented in this document reflect the latest public health thinking and scientific evidence as of April 2021. You are advised that the COVID-19 vaccine landscape remains highly fluid, and it is your responsibility to ensure that decisions are made based on the most up-to-date information available. Partners In Health does not provide medical advice, diagnosis, or treatment in the United States. Always seek the advice of a physician or other qualified healthcare provider with any questions regarding a medical condition. The information, including but not limited to text, graphics, images, and other material contained in this document, are intended for informational purposes only.

## 1. Calculator
Site Modelling for Covid-19 vaccination of local residents
| User notes | Assumptions |  |  | Site modelling outputs |  |  | User Notes
|  | -Timeline represents weeks from commencement of phase1b - HCW vaccinations at UH not included -For all throughput, assume 8 hours per day 6 days per week except for UH site -No children under 18 to be vaccinated in first 6 months -Nursing home residents to be vaccinated by retail pharmacy partners |  |  | Type | Number of sites | Weekly capacity for locality | Formula
[5 empty] | Site type 1 Hospital | 1 | 3000 | =c26
[5 empty] | Site type 2 (small, DOH/FQHC) | 2 | 1500 | =c33*I8
[5 empty] | NEW SITE TYPE | 1 | 1843.2 | =C48*I9
[5 empty] | Total weekly vaccinations for locality |  | 6343.2 | =sum(k8:k10)
| User notes | Population to be vaccinated
| Formula | Number | Type | Notes |  |  | weeks
| Input | 100000 | Local residents |  | Time to vaccinate 100% |  | 20.4944 | =c19/k11
| Input | 30000 | Local residents under 16 or 18 | Unable to vaccinate based on eligibility | Time to vaccinate 85% |  | 17.4202 | =c20/k11
| Input | 5000 | Local residents in nursing homes | Coverage provided by retail pharmacy partners |  |  | Target <24 weeks
| =c13-c14-c15 | 65000 | Total people to be vaccinated in next 6 months | Exclude minors & nursing homes
| =c17*2 | 130000 | Total vaccines to be delivered in next 6 months for 100% coverage | Assume 2 dose until J&J received
| =c17*.85*2 | 110500 | Total vaccines to be delivered in next 6 months for 85% coverage | Assume 2 dose until J&J approved
Staffing needs for new site
[5 empty] | Cadre | Weekly # needed | Weekly compensation |  | User Notes
|  | Site types: Throughput and Staffing |  |  | Nurses | 10 | 18000 |  | Type of nurse
| User notes | Site type 1 - Large hospital (assume scale up to gen pop after phase 1a) |  |  | Pharmacists | 2 | 4400 |  | RN | <select one
|  | Throughput |  |  | Admin - registration | 5 | 3200
|  | 1000 | Daily throughput |  | Admin - data entry/QA | 7 | 4200
|  | 3000 | Weekly throughput |  | Site coordinator | 2 | 5200
|  | Weekly Staffing |  |  | Nursing Supervisor | 2 | 5200
|  | 0 | All staffing to be provided by hospital |  | Safety officers (EMT) | 2 | 3600
[5 empty] | External safety - patrol & security | 4 | 7200 |  | Source of safety staff
| User notes | Site type 2 - Small (FQHC size) | [6 empty] | Dept PS | <select one
|  | Throughput | based on 8-seat model, 3 clients per chair per hour |  | Total weekly costs for model | 34 | 51000
|  | 125 | Daily throughput
|  | 750 | Weekly throughput
Weekly Staffing
|  | 5 | Nurses
|  | 2 | Pharmacists
|  | 3 | Admin - registration
|  | 5 | Admin - data entry/QA
|  | 2 | Site coordinator
|  | 2 | Nursing Supervisor
|  | 2 | Safety officers (EMT)
|  | 4 | External safety - patrol & security
| User Notes | Site type 3 - Medium (School gym/large conference room)
| Formula | Throughput | based on 16-seat model, 3 clients per chair per hour
| ='Throughput model - medium site'!N11 | 307.2 | Daily throughput
| =c47*6 | 1843.2 | Weekly throughput
Weekly Staffing
| ='Staffing estimates'!M7 | 10 | Nurses
| ='Staffing estimates'!M8 | 2 | Pharmacists
| ='Staffing estimates'!M9 | 5 | Admin - registration
| =SUM('Staffing estimates'!M10:M11) | 7 | Admin - data entry/QA
| ='Staffing estimates'!M4 | 2 | Site coordinator
| ='Staffing estimates'!M5 | 2 | Nursing Supervisor
| ='Staffing estimates'!M^ | 2 | Safety officers (EMT)
| =SUM('Staffing estimates'!M14:M15) | 4 | External safety - patrol & security
Enter data in orange boxes only!
Enter data in orange boxes only!
Enter data in orange boxes only!
Enter data in orange boxes only!
Note on B5: Fill in assumptions for your local context, based on conversations with stakeholders.
Note on K5: Time to % coverage achievement is contingent on combined coverage of all local entities involved.
Note on B11: Enter estimates based on conversations with stakeholders, eligibility requirements, and any populations already vaccinated/already accounted for in vaccination planning.
Note on L21: In the dropdown option (cells L23 and L30) toggle to adjust staff type, and resulting compensation.
Note on B23: Document other coverage sources. Determine estimated quantities of vaccine coverage already in process by seeking informaiton from other community stakeholders involved in vaccination.
Note on B30: Document other coverage sources. Determine estimated quantities of vaccine coverage already in process by seeking informaiton from other community stakeholders involved in vaccination.
Note on B45: These data are supplied by the information on tabs 2. and 3.

## 2. Staffing estimates
User notes
|  |  | # | hrs/day | hrs/wk | hrs needed | hrs total | hrs remain | FTE+ | Total | Weekly Total
Total Staff Per Shift for 16 seat clinic | Command Staff | Clinic Manager (Site Coordinator) | 1 | 8 | 40 | 48 | 40 | 8 | 0.2 | 1.2 | 2
|  | Nurse Supervisor (Clinical Branch lead) | 1 | 8 | 40 | 48 | 40 | 8 | 0.2 | 1.2 | 2
|  | Safety Officer (EMT) | 1 | 8 | 40 | 48 | 40 | 8 | 0.2 | 1.2 | 2 |  | Reg | Reg | Reg | Reg
| Clincal Branch | Nurses | 8 | 8 | 40 | 384 | 320 | 64 | 1.6 | 9.6 | 10
|  | Pharmacist* | 1 | 8 | 40 | 48 | 40 | 8 | 0.2 | 1.2 | 2 |  | Q mgmt |  | Q mgmt |  | Safety
| Administrative Branch | Registration staff | 4 | 8 | 40 | 192 | 160 | 32 | 0.8 | 4.8 | 5 | RN spvsr
|  | Data Entry | 3 | 8 | 40 | 144 | 120 | 24 | 0.6 | 3.6 | 4 |  | Px | Px | Px | Px
|  | Q management | 2 | 8 | 40 | 96 | 80 | 16 | 0.4 | 2.4 | 3
|  | * or additional nurse | [9 empty] | Px |  | RN | RN |  | Px
[12 empty] | Px | RN |  |  | RN | Px
| External Staff | Public Safety patrol | 1 | 12 | 60 | 72 | 60 | 12 | 0.3 | 1.3 | 2 | Px | RN |  |  | RN | Px
|  | Security guard | 1 | 12 | 60 | 72 | 60 | 12 | 0.3 | 1.3 | 2 | Px |  | RN | RN |  | Px
Total Daily Staff for 16 seat clinic (not incl schedulers) |  |  | 23 | Total Weekly Staff for 16 seat clinic | [6 empty] | 34 |  | Px | Px | Px | Px
Pharm
[13 empty] | Data | Data | Data
|  |  | # | hrs/day | hrs/wk | hrs needed | hrs total | hrs remain | FTE+ | Total | Weekly Total
Total Staff Per Shift for 8 seat clinic | Command Staff | Clinic Manager (Site Coordinator) | 1 | 8 | 40 | 48 | 40 | 8 | 0.2 | 1.2 | 2 | Security |  | Pub Safety |  |  | Clinic Mgr
|  | Nurse Supervisor (Clinical Branch lead) | 1 | 8 | 40 | 48 | 40 | 8 | 0.2 | 1.2 | 2
|  | Safety Officer (EMT) | 1 | 8 | 40 | 48 | 40 | 8 | 0.2 | 1.2 | 2
| Clincal Branch | Nurses | 4 | 8 | 40 | 192 | 160 | 32 | 0.8 | 4.8 | 5 | 8 Seat Clinic
|  | Pharmacist* | 1 | 8 | 40 | 48 | 40 | 8 | 0.2 | 1.2 | 2 |  | Reg | Reg | Reg
| Administrative Branch | Registration staff | 2 | 8 | 40 | 96 | 80 | 16 | 0.4 | 2.4 | 3
|  | Data Entry | 2 | 8 | 40 | 96 | 80 | 16 | 0.4 | 2.4 | 3 |  | Q mgmt |  |  |  | Safety
|  | Q management | 1 | 8 | 40 | 48 | 40 | 8 | 0.2 | 1.2 | 2 | RN spvsr
|  | * or additional nurse | [10 empty] | Px | Px
| External Staff | Public Safety patrol | 1 | 12 | 60 | 72 | 60 | 12 | 0.3 | 1.3 | 2 |  |  | RN |  | Px
|  | Security guard | 1 | 12 | 60 | 72 | 60 | 12 | 0.3 | 1.3 | 2 |  |  |  | RN | Px
| Off site | Schedulers (cross sites) | 7 | 8 | 40 | 336 | 280 | 56 | 1.4 | 8.4 | NA | Px | RN
Total Daily Staff for 8 seat clinic (not incl schedulers) |  |  | 15 | Total Weekly Staff for 8 seat clinic | [6 empty] | 25 | Px |  | RN
[13 empty] | Px | Px
Pharm
[13 empty] | Data | Data
[12 empty] | Security |  | Pub Safety |  |  | Clinic Mgr
User notes
DO NOT MOVE/EDIT BELOW
Salary info
Hourly rate | Cadre
40 | LPN
45 | RN
18 | CMA
55 | Nurse+hazard pay
55 | Pharmacists
65 | Site coordinator
65 | Nursing Supervisor
16 | Admin - registration
15 | Admin - data entry/QA
45 | Dept PS
22 | School Guards
DPS | Public safety costs
45 | Safety officers (EMT) N/A
45 | External safety – security – N/A
Crossing | Public safety costs
22 | Safety officers (EMT) N/A
22 | External safety – security – N/A
Enter data in orange boxes only!
Enter data in orange boxes only!
Note on D2: Modify the inputs based on information from the Throughput models (blue tabs), and other staffing needs for administration, data entry, safety, and management. Make sure to adjust daily hours based on role descriptions.
Note on B55: Update based on local rates/information

## 3.Throughput model - med site
| Seat 1 | Seat 2 | Seat 3 | Seat 4 | Seat 5 | Seat 6 | Seat 7 | Seat 8
Pre-Seat | Registration | Registration | Registration | Registration | Registration | Registration | Registration | Registration |  |  | User notes
5 min | Seat 1: Vaccinate; Seat 5: Vaccinate | Hours of Operation | 9:00a - 5:00pm | Formula
10 min | Seat 1: Observe; Seat 2: Vaccinate; Seat 5: Observe; Seat 6: Vaccinate | Total Hours | 8
15 min | Discharge | Observe | Vaccinate |  | Discharge | Observe | Vaccinate |  | Days per week | 6
20 min | Sanitize | Discharge | Observe | Vaccinate | Sanitize | Discharge | Observe | Vaccinate | Total hourly throughput | 38.4 | =(48*60)/75
25 min | Vaccinate | Sanitize | Discharge | Observe | Vaccinate | Sanitize | Discharge | Observe | Total daily throughput | 307.2 | =m10*m8
30 min | Observe | Vaccinate | Sanitize | Discharge | Observe | Vaccinate | Sanitize | Discharge | Total Weekly throughput | 1843.2 | =m11*m9
35 min | Discharge | Observe | Vaccinate | Sanitize | Discharge | Observe | Vaccinate | Sanitize
40 min | Sanitize | Discharge | Observe | Vaccinate | Sanitize | Discharge | Observe | Vaccinate
45 min | Vaccinate | Sanitize | Discharge | Observe | Vaccinate | Sanitize | Discharge | Observe
50 min | Observe | Vaccinate | Sanitize | Discharge | Observe | Vaccinate | Sanitize | Discharge
55 min | Discharge | Observe | Vaccinate | Sanitize | Discharge | Observe | Vaccinate | Sanitize |  | Site layout viewed from above:
60 min | Sanitize | Discharge | Observe | Vaccinate | Sanitize | Discharge | Observe | Vaccinate
65 min |  | Sanitize | Discharge | Observe |  | Sanitize | Discharge | Observe
70 min | Seat 3: Sanitize; Seat 4: Discharge; Seat 7: Sanitize; Seat 8: Discharge
75 min | Seat 4: Sanitize; Seat 8: Sanitize
| Seat 9 | Seat 10 | Seat 11 | Seat 12 | Seat 13 | Seat 14 | Seat 15 | Seat 16
Pre-Seat | Registration | Registration | Registration | Registration | Registration | Registration | Registration | Registration
5 min | Seat 9: Vaccinate; Sanitize Seat 13: Vaccinate
10 min | Seat 9: Observe; Seat 10: Vaccinate; Sanitize Seat 13: Observe; Sanitize Seat 14: Vaccinate
15 min | Discharge | Observe | Vaccinate |  | Discharge | Observe | Vaccinate
20 min | Sanitize | Discharge | Observe | Vaccinate | Sanitize | Discharge | Observe | Vaccinate
25 min | Vaccinate | Sanitize | Discharge | Observe | Vaccinate | Sanitize | Discharge | Observe
30 min | Observe | Vaccinate | Sanitize | Discharge | Observe | Vaccinate | Sanitize | Discharge
35 min | Discharge | Observe | Vaccinate | Sanitize | Discharge | Observe | Vaccinate | Sanitize
40 min | Sanitize | Discharge | Observe | Vaccinate | Sanitize | Discharge | Observe | Vaccinate
45 min | Vaccinate | Sanitize | Discharge | Observe | Vaccinate | Sanitize | Discharge | Observe
50 min | Observe | Vaccinate | Sanitize | Discharge | Observe | Vaccinate | Sanitize | Discharge
55 min | Discharge | Observe | Vaccinate | Sanitize | Discharge | Observe | Vaccinate | Sanitize
60 min | Sanitize | Discharge | Observe | Vaccinate | Sanitize | Discharge | Observe | Vaccinate
65 min |  | Sanitize | Discharge | Observe |  | Sanitize | Discharge | Observe
70 min | Seat 11: Sanitize; Sanitize Seat 12: Discharge; Sanitize Seat 15: Sanitize; Sanitize Seat 16: Discharge
75 min | Sanitize Seat 12: Sanitize; Sanitize Seat 16: Sanitize
Note on N6: Modify based on site capacity, and likely hours of operation.
Enter data in orange boxes only!

## 4.Throughput model - small site
| Seat 1 | Seat 2 | Seat 3 | Seat 4
Pre-Seat | Registration | Registration | Registration | Registration | 4 seats
5 min | Vaccinate |  | Vaccinate |  | Hours of Operation | 9:00a - 5:00pm | Site layout viewed from above:
10 min | Observe | Vaccinate | Observe | Vaccinate | Total Hours | 8
15 min | Discharge | Observe | Discharge | Observe | Days per week | 6
20 min | Sanitize | Discharge | Sanitize | Discharge | Total hourly throughput | 11.0769
25 min | Vaccinate | Sanitize | Vaccinate | Sanitize | Total daily throughput | 88.6154
30 min | Observe | Vaccinate | Observe | Vaccinate | Total Weekly throughput | 531.6923
35 min | Discharge | Observe | Discharge | Observe
40 min | Sanitize | Discharge | Sanitize | Discharge
45 min | Vaccinate | Sanitize | Vaccinate | Sanitize
50 min | Observe | Vaccinate | Observe | Vaccinate
55 min | Discharge | Observe | Discharge | Observe
60 min | Sanitize | Discharge | Sanitize | Discharge
65 min |  | Sanitize |  | Sanitize
8 seats
| Seat 5 | Seat 6 | Seat 7 | Seat 8 | Hours of Operation | 9:00a - 5:00pm
Pre-Seat | Registration | Registration | Registration | Registration | Total Hours | 8
5 min | Vaccinate |  | Vaccinate |  | Days per week | 6
10 min | Observe | Vaccinate | Observe | Vaccinate | Total hourly throughput | 22.1538
15 min | Discharge | Observe | Discharge | Observe | Total daily throughput | 177.2308
20 min | Sanitize | Discharge | Sanitize | Discharge | Total Weekly throughput | 1063.3846
25 min | Vaccinate | Sanitize | Vaccinate | Sanitize
30 min | Observe | Vaccinate | Observe | Vaccinate
35 min | Discharge | Observe | Discharge | Observe
40 min | Sanitize | Discharge | Sanitize | Discharge
45 min | Vaccinate | Sanitize | Vaccinate | Sanitize
50 min | Observe | Vaccinate | Observe | Vaccinate
55 min | Discharge | Observe | Discharge | Observe
60 min | Sanitize | Discharge | Sanitize | Discharge
65 min |  | Sanitize |  | Sanitize
Enter data in orange boxes only!